## Sheet1
Task | Owner | Due date
Send .Tar to group | Brenton | 2016-03-23
Consider how to package - Jason Troopy and Greg Smith on content creation | Kanaya / Wayne | 2016-03-30
Develop & Document Use Case(s) - examples below to Brenton - Find frequency of beaconing - Whitelisting | Wayne, Matt | 2016-03-23
Brenton to modify appropriate code (NW only) | Brenton | TBD
Placeholder for next task
Placeholder for next task
Placeholder for next task
Go / No Go Meeting
Visualization - Needed? | Wayne | 4/15?
PPT - who, how, what, where | Greg | 2016-04-15
Final run through with team | APAC team | 2016-04-22
Assumptions:
1) For TAM week, MVP product
2) For Matt G`s work, use Use Cases (eg. Whitelist). Where is this list of Use cases?
3) In scope only Network Use Cases